## Sheet1
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | Set up Maven-based project with proper folder structure for dependency management. | MUST HAVE | None | Tushar Yadav | Done
Sprint 1 | Sprint 1 | US02 | Configure Tomcat server and deploy WAR to verify servlet deployment. | MUST HAVE | US01 | Tushar Yadav | Done
Sprint 2 | Sprint 2 | US03 | Establish MySQL database connection using JDBC for banking database. | MUST HAVE | US02 | Tushar Yadav | Done
Sprint 2 | Sprint 2 | US04 | Implement user registration module with validation and DAO integration. | MUST HAVE | US03 | Tushar Yadav | Done
Sprint 3 | Sprint 3 | US05 | Secure user login functionality to prevent unauthorized access. | MUST HAVE | US04 | Tushar Yadav | Done
Sprint 3 | Sprint 3 | US06 | View account balance functionality with proper API response. | SHOULD HAVE | US04 | Tushar Yadav | Done
Sprint 4 | Sprint 4 | US07 | Transfer funds between accounts with validation for sufficient balance. | MUST HAVE | US05 | Tushar Yadav | Done
Sprint 5 | Sprint 5 | US08 | Implement transaction history retrieval for users. | SHOULD HAVE | US06 | Tushar Yadav | Done
Sprint 6 | Sprint 6 | US09 | Add exception handling and logging for all APIs and services. | MUST HAVE | US07 | Tushar Yadav | Done
Sprint 6 | Sprint 6 | US10 | Expose REST APIs for account and transaction management. | COULD HAVE | US08 | Tushar Yadav | Done