## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Tushar Yadav | 2025-09-12 | Maven build fails due to missing Spring Boot starter dependency | Sprint 1 | Tushar Yadav | Configuration | Added missing Spring Boot starter dependency in pom.xml | 2025-09-12 | Closed | Build successful
2 | Tushar Yadav | 2025-09-14 | Application unable to connect to MySQL due to incorrect credentials | Sprint 1 | Tushar Yadav | Logical | Updated application.properties with correct DB username/password | 2025-09-15 | Closed | Connection verified
3 | Tushar Yadav | 2025-09-16 | NullPointerException in UserService when user not found | Sprint 2 | Tushar Yadav | Logical | Added null checks and custom UserNotFoundException | 2025-09-17 | Closed | Verified with test cases
4 | Tushar Yadav | 2025-09-18 | REST API returns 500 error on invalid input | Sprint 2 | Tushar Yadav | Standards | Added @Valid annotations and exception handling in controller | 2025-09-18 | Closed | API returns proper 400 status now
5 | Tushar Yadav | 2025-09-21 | Duplicate entries allowed in registration | Sprint 2 | Tushar Yadav | Logical | Added pre-insert check for existing email/username | 2025-09-22 | Closed | Duplicate prevented successfully
6 | Tushar Yadav | 2025-09-24 | Logs not showing during application runtime | Sprint 3 | Tushar Yadav | Maintainability | Configured Logback logging properly | 2025-09-25 | Closed | Logs verified
7 | Tushar Yadav | 2025-09-27 | Transaction rollback not working on exception | Sprint 3 | Tushar Yadav | Logical | Annotated service method with @Transactional | 2025-09-28 | Closed | Rollback verified
8 | Tushar Yadav | 2025-10-01 | Frontend unable to parse LocalDate fields from API | Sprint 4 | Tushar Yadav | Configuration | Added jackson-datatype-jsr310 dependency and JavaTimeModule registration | 2025-10-01 | Closed | Dates now parsed correctly
9 | Tushar Yadav | 2025-10-03 | API returning inconsistent HTTP status codes | Sprint 4 | Tushar Yadav | Standards | Standardized response codes and messages across controllers | 2025-10-04 | Closed | Verified with Postman
10 | Tushar Yadav | 2025-10-05 | Email service throws rate limit error | Sprint 5 | Tushar Yadav | Configuration | Added delay between sending emails to respect SMTP limits | 2025-10-06 | Closed | Emails sent successfully
11 | Tushar Yadav | 2025-10-08 | Incorrect SQL query in update operation | Sprint 5 | Tushar Yadav | Code (SQL) | Fixed syntax error in UPDATE query | 2025-10-08 | Closed | Verified via test database
12 | Tushar Yadav | 2025-10-10 | Withdrawal allows negative balance | Sprint 5 | Tushar Yadav | Logical | Added validation to prevent negative balance | 2025-10-11 | Closed | Verified with test transactions